## Task Breakdown
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Create user stories list | 2025-03-14 | 2025-03-18
2 | Brainstorm website layout/ create wireframes | 2025-03-15 | 2025-03-18
3 | Create list of content (fonts, logos, colors) | 2025-03-16 | 2025-03-18
4 | Set up basic HTML structure | 2025-03-17 | 2025-03-18
5 | Create homepage layout with navigation and footer | 2025-03-17 | 2025-03-18
6 | Build About page | 2025-03-20 | 2025-03-25
7 | Build Group Information Page | 2025-03-21 | 2025-03-25
8 | Build Gift Shop Page | 2025-03-22 | 2025-04-02
9 | Build Contact Form Page | 2025-03-23 | 2025-04-02
10 | Add APIs | 2025-03-24 | 2025-04-02
11 | Finish Styling
12 | Finish javascript
13
14
15
...